## Sheet1
Suspense | CHLOE Action Item | Assigned to | Status
As of 1 Aug 08
2008-07-18 | CH PMO requested map of China Lake Complex (Gary Ayers) | Gary Ayers | Complete
2008-07-18 | Plan to conduct familiarization flights (CH flights below FL180) | Gary Ayers | Complete
2008-07-20 | Obtain Flight line access for CHLOE Team, 21-22 Jul 08 | Gary Ayers | Complete
2008-07-22 | Provide data sets for raw uncompressed (.mhs) as well as processed products (JPEG2000) | Constant Hawk Program Management Office | Complete
2008-07-22 | Conduct a site survey at China Lake, now 21-22 Jul 08. | Constant Hawk Program Management Office | Complete
2008-08-08 | Sample CH Data to NGA for HSG Accreditation | Pixia, CH PMO | Open
2008-07-22 | Systems Elevation & System Requirements | JFCOM VA, (I3),CH PMO | Complete
2008-07-25 | Provide details on size and amount of equipment and space and fuel requirements) | Constant Hawk Program Management Office | Complete
2008-07-25 | Send 3 Disk sets to CH PMO (Call Bill Miller at (410) 713-0493 for address) | Gilles Van Neederveen / Eric Craig/Louis Miller | Complete
2008-07-25 | NGA need to know if it would be quicker to FedEx disks than to move a full 6 TBytes across a line | Constant Hawk Program Management Office | Complete
2008-07-25 | Need a block of rooms to accommodate personnel- Need # from JFCOM (Gov and Contractor) | CDR Smith negotiating with hotel | Open
2008-07-25 | HSG Guard connectivity to network / Provide sample data to CDR Smith) | Constant Hawk Program Management Office | Complete
2008-07-25 | Provide CH Admin Security Info to CHLOE team | Bernie | Complete
2008-07-25 | Airspace Decision Brief | NGA/NAWC | Complete (will use Inyokern)
2008-08-28 | Obtain cost estimates and BOE from LOGOS | CH PMO | Complete
2008-07-29 | JFCOM conduct Site visit to PSL | CDR Florence / Larry Diaz / Dan Bagley | Complete
2008-07-30 | Provide a detailed drawing of communications arch to Dave Tolerton | Charles Wiggens | Complete
2008-08-06 | Complete Security accreditation package | Dave Tolerton | Open
2008-08-06 | DSAWG Notification (informal notification given) | NGA | Open
2008-08-08 | VA accreditation Paperwork to Dr. Miller | JFCOM, CH PMO | Open
2008-08-06 | Provide all existing accreditation paper work associated with system (Comms, terminals, etc) | Constant Hawk Program Management Office – Bill Hughes and Rebbecca (732) 532-4446 will get sample data to PSL | Open
2008-08-06 | NGA needs information on any potential accreditation to include; any existing paperwork accreditation and frequency clearance for that link. Specific format and transport protocol for the live data is still TBD at this point, but the CH program office agreed to sending data down to the GCS in a commercially-available streaming format (i.e. MPEG2). | Constant Hawk Program Management Office | Open
2008-08-08 | Arrange ramp space for one (two?) aircraft at Inyokern, ground support equipment, maintenance trailer, and O2 for aircrews. Working GSE from CL, backup plan is to use commercial rentals from Lancaster, CA | CDR Smith/Gary Ayers | Open; free ramp and office space secured with Scott Seymour, General Manager Inyokern Airport if fuel is purchased from Scott; however NAWS China Lake cannot provide GSE; backup plan to lease GSE must be enabled
2008-08-08 | Check on LSRS availability to support CHLOE testing, as a backup to LynxSAR | CDR Smith | Open; P-3 LSRS is not available (Closed)
2008-08-06 | Provide test plan and scenarios within next couple weeks | Constant Hawk Program Management Office | Open
2008-08-01 | Complete CH PMO Schedule | Constant Hawk Program Management Office | Complete
2008-08-01 | CH CONOPS (Updated) | Constant Hawk Program Management Office | Complete
2008-08-06 | VIP RSVP (Include CH Site visit) | JFCOM | Open
2008-08-08 | JFCOM network diagrams | JFCOM | Open
2008-08-01 | CH requested maps of area of operation | Gary Ayers | Complete
2008-08-08 | Valiant Angel Network accreditation paperwork to JFCOM DAA | JFCOM CDR Florence | Open
2008-08-01 | Email center point of CH collection to CDR Florence | Gary Ayers | Complete
2008-08-06 | RTN Support (MHT) | NGA (CDR Smith) | Complete
2008-08-06 | RTN Support (DIB, HSG) | NGA (CDR Smith) | Open
2008-08-01 | nui sample data | CDR Smith will check with Dr Miller | Complete
2008-08-04 | DDTE Notification 2 weeks notice required | NGA | Complete
2008-08-08 | Need Air Worthiness Certificates and Pilot Certifications (CH PMO) Is this still required? | Constant Hawk Program Management Office | Complete; not required due to bed-down from IYK
2008-08-08 | Develop approaches/options for “with” and “without” data link | Dan, Larry, Dwayne | Open
| DCGS-I - CDR Smith will work with Dave Wall | CDR Smith | Complete
2008-08-05 | Determine if we can use CH contract for Logos' work | CH PMO (Hanscom) | Open
TBD | Coordinate passing of funds for Logos' work (pending completion of AI above) | NGA (CDR Smith) | Open
2008-08-08 | Formulate plan/obtain resources to collect ground truth from JFCOM rental vehicles | Gary Ayers | Open; currently working with Louis Miller on possibility of outfiting two rental vehicles with GPS
2008-08-06 | Coordinate with CH PMO on data production needs and delivery specifications | Dan Bagley | Open
2008-08-08 | Provide live link spec data to Gary Ayers, Dr Miller | CH PMO via Logos | Open; DD Form 1494 is still required and getting critical as information was not provided during EC08 planning
| Provide complete Raytheon team listing and contact info to add to distribution | Marcos | Complete
| Add Raytheon team to distribution list | Dan/Bernie | Complete
2008-08-08 | New DDTE paperwork to DDTE Mgt Office | Dave Tolerton | Open
2008-08-08 | Explore possibility of tapping CFBLnet in R2 for PSL, instead of having them operate out of R3 | Joe Smith | Open
2008-08-12 | Coordinate participation for U-2 ASARS-2A (Tuesday 19 Aug 08/Thursday 21 Aug 08) and RQ-4 (Wednesday 20 Aug 08) platforms | Gary Ayers and 9th Ops Group (Ken Hall) | Open; pending 9th OG MEGA Meeting on Tue, 12 Aug 08